## Risks
Study Abroad Management System (SAMS)
Risk | Risk Resolution Measures | Justification
Sometimes the search will not list the proper programs if searching by a specific category or semester | Ensure that all options are identified in the code to allow for those searched items to be seen | Include all searchable programs. There are times that we will need to add in any new or delete any programs that aren't listed anymore, but having that information updated on a bi-weekly review will help identify any of those programs that may have been added or deleted
Some countries aren't listed even though they are stated on the website | Include all countries in the search and allow for them to be viewed and clicked. Some countries may have the same 3 letter ID code. In this case, a list of multiple countries with those letters will all be displayed | This allows for the students to find the correct country when applying. It doesn't serve any justice with having an individual search for a country that isn't listed. It limits the amount of applicants that submit
Occassionally the user can't login into the system | Display a login message stating that "CAPS LOCK" is pressed | If the member is aware of them typing in the wrong password, it will prevent them from being locked out after the 3rd attempt. This will reduce the time it will take for individuals to have a new password created everytime they unsuccessfully logs in
The applications once submitted will not process in the site, there is an error message that pops up after member clicks submit button | Do a test run and see why the error is being displayed. There may be some execution error within the code to display the proper forwarding link to allow for the website to have the information saved correctly | Sometimes the link may not be the correct one for information to be sent. We will need to ensure that it is properly working first before the project is finished so that we will have the applications sent to the faculty. If we can get that fixed as soon as possible, it won't prevent the applications from not being submitted.
Site times out member and logs them out after being logged in with no activity for 3 minutes | Come up with an option to allow more time, maybe at least 30 minutes of inactivity or have it disabled altogether. If you choose to disable the inactivity of the site, you will need to be aware of the security measures of doing so and possibly making it unsafe for the member to leave their system logged in when they aren't around their system. | Having more time to not be active in the website without logging out an individual is better than having them login every 3 minutes.There may be a time where the individual needs to go find information to complete a specific task needed to complete an application process. Increasing the time of inactivity would be the best way to go to ensure that the individual is able to do all the necessary actions that are required without them being logged out and possibly losing the data that they may have typed.